## Slide 1: Owensboro Autism Network: Water Balloon Bash
Emily Haimes, Faith Porter, Grace Bush, Mallory Richards, Savana Canary

## Slide 2
Project Summary
What’s the plan?
  Our plan is to hold a water balloon tournament at Ben Hawes Park on Saturday, May 21st.
  Our goal is to raise money and spread awareness for Owensboro Autism Network.
  After budgeting, we ask for $300 to make our plan happen.

## Slide 3: What is Autism Spectrum Disorder?
Autism Spectrum Disorder
  Developmental condition which affects individuals in two main areas: communication and social interaction.
  Restricted, repetitive patterns of behavior, interests or activities.
Owensboro Autism Network
  Founded in July 2013
  Co-Directors: Sandra Hammers and Whitney Logsdon
  1 of 12 non-profit organizations located in the Ronald E. Logsdon Community Center.
  Provides trainings, information, assistance, and disability-friendly activities for families affected by Autism Spectrum Disorder.

## Slide 4
Source: AAP, Economic Burden of Childhood Autism Spectrum Disorders (2014)

## Slide 5: The Identified Need
1 in 68 children has been identified with autism spectrum disorder (CDC 2014)
Approximately one in 42 boys and one in 189 girls living in the ADDM (Autism and Developmental Disabilities Monitoring) Network communities were identified as having ASD (CDC 2014)
31% of children with ASD were classified as having IQ scores in the range of intellectual disability (CDC 2014)

## Slide 7: This pie chart shows percent distribution of child’s age when their parent or guardian was first told that their child had autism spectrum disorder among children aged 6-17 years.
Source: CDC/NCHS, Survey of Pathways to Diagnosis and Services (2011)

## Slide 8: Project Description
Host a water balloon bash to help raise money and awareness for the Owensboro Autism Network
Location
  Ben Hawes Park
  Run from 8:00 A.M. to 12:00 P.M. on May 21th, 2016
Tournament play
  Teams of 4-8 people
  Admittance fee of $5 per person (if signed up by May 13th)
  Late sign up from May 14 - May 18, $8.00 per person
Recreational Play
  Different field
  All ages allowed
  Admittance fee and its terms will remain the same

## Slide 9: Project Description (cont.)
Snacks
  Bananas, apples, and water provided to everyone
  Located inside shelter
No bathing suits allowed
  Community project
  All-age groups
    Track/basketball shorts
    Tank tops
    T-shirts

## Slide 10: Objectives
Hold a water balloon bash with approximately 100 participants.
Raise money for Owensboro Autism Network from the registration fees and t-shirt sells.
Every participant will leave aware of the autism community in the Daviess County Region.

## Slide 11: Target Audience & Partner Organizations
Target Audience
  We plan to reach the people of Daviess County. Our goal is to reach 500 people, either in attendance, buyer of a t-shirt, or through social media advertising.
Partner Organizations
  Owensboro Autism Network
  Ben Hawes Park
  Terry’s Tees
  Creation Gardens Produce

## Slide 12: How Will Your Project Help?
Raise money for Owensboro Autism Network (OAN)
  T-shirt money and admission fees from the water balloon tournament
Raise awareness for Owensboro Autism Network and Autism
  Talking to elementary and middle schools, flyers around town , advertising OAN on the shirts

## Slide 13: Timeline
March
  Contact all venues, Terry's Tees, and any other possible sponsors
  Apply for grant 3/16
  Present powerpoint to expert panel 3/31
April
  Make purchases and finalize the venues
  Set a deadline for online registration 5/13
  Allow people to register 4/13
  Sign up LSA volunteers
May
  Contact participants a week before with reminders and ensure that we have all materials needed 5/13-5/14
  Fill up water balloons the day before the bash 5/20
  Meet early the day of the bash and set everything up at Ben Hawes 5/21
  Welcome and register the guests 5/21

## Slide 14: Roles and Responsibilities & Community Collaboration
ROLES AND RESPONSIBILITIES
  We expect LSA students to sign up for one hour shifts and be prepared to help set up the event, help run it, and then clean up afterwards.
COMMUNITY COLLABORATION
  We plan to work with the the Owensboro Autism Network. We have been in contact with Whitney Logsdon, the co-director of the network. She has been very enthusiastic and will be promoting the event as well.
  We plan to host the Water Balloon Bash at Ben Hawes Park, and we will be renting one of the shelters. We have been in contact with Amanda Rogers, Director of Parks and Recreations, and she has instructed us to fill out an Special Event Application.

## Slide 15: Obstacles
If Ben Hawes isn't available, we plan to use Southern Oaks or Audubon
If people get injured, we will have waivers that say we are not responsible
If the weather isn't appropriate, we will reschedule for another date
If we don't have enough people sign up, we will revert to making the money through selling T-shirts

## Slide 16: Budget

## Slide 17: Potential Funding Sources

## Slide 18: Conclusion
Our project will consist of raising money and spreading awareness for the Owensboro Autism Network by hosting a Water Balloon Bash at Ben Hawes Park on May 21st.
Our goal is to reach 500 people through the process of distributing flyers, selling t-shirts, and hosting a tournament water balloon fight and to raise $1,000 to donate to the Owensboro Autism Network.
We estimate that this project will cost us $298.10 out of the $500 given to us from the Life Science Academy grant. The remainder will be given to the Owensboro Autism Network.
Check out our website! http://oanwaterballoonbash.weebly.com/

## Slide 19
http://oanwaterballoonbash.weebly.com/

## Slide 20: THANK YOU to our expert panel, community collaborations, and our possible sponsors. QUESTIONS?